## Sheet1
Ward | Block | Postcode | ertic | Notes | Number of units | Provider
Arsenal | DEEPDALE | N4 2EH | Cabling complete | Waiting for network build | 20 | Hyperoptic
Arsenal | TAWNEY COURT | N5 1AS | Cabling complete | Waiting for network build | 24 | Hyperoptic
Arsenal | VAUDEVILLE COURT | N4 2QG | Survey pack approved | No installation timetable provided as yet | 36 | Hyperoptic
Arsenal | GILLESPIE ROAD ESTATE | N5 1LG | Survey pack approved | Awaiting installation dates | 18 | Community Fibre
Bunhill | CYRUS HOUSE | EC1V 0BU | Cabling complete | Waiting for network build | 39 | Hyperoptic
Bunhill | KESTREL HOUSE | EC1V 8EL | Live connections available |  | 106 | Community Fibre
Bunhill | LAGONIER HOUSE | EC1V 3TJ | Live connections available |  | 24 | Hyperoptic
Bunhill | PLEYDELL ESTATE | EC1V 3SN | Cabling complete | Waiting for network build | 102 | Hyperoptic
Bunhill | REDBRICK ESTATE | EC1V 3QL | Works on site | Amended survey pack received to include new build. Start date 16 November, | 102 | Hyperoptic
Bunhill | THE TRIANGLE | EC1V 0AR | Cabling completed except 94-130 | Waiting for network build | 130 | Hyperoptic
Bunhill | WENLAKE ESTATE | EC1V 3PX | Live connections available |  | 29 | Hyperoptic
Bunhill | CHADWORTH HOUSE ESTATE | EC1V 3RQ | Survey pack approved | Works commencing in November | 70 | Hyperoptic
Bunhill | GAMBIER ESTATE | EC1V 8EH | Cabling complete | Waiting for network build | 115 | Community Fibre
Bunhill | ST LUKES ESTATE | EC1V 8EH | Works on site | Works commencing in November | 128 | G-Network
Bunhill | STAFFORD CRIPPS | EC1V 9ES | Cabling complete | Waiting for network build | 60 | Hyperoptic
Bunhill | WHITBREAD ESTATE | EC1Y 8TD | Cabling complete | Waiting for network build | 60 | Hyperoptic
Bunhill | COLTASH COURT | EC1V 8TD | Survey packs submitted | Technical considerations being considered by delivery team | 65 | Hyperoptic / Community Fibre
Bunhill | BANNER ESTATE | EC1Y 8NQ | Survey pack approved | Awaiting installation dates | 15 | Hyperoptic
Bunhill | GEORGE GILLETT COURT | EC1Y 8QH | Survey pack approved | Awaiting installation dates | 17 | Hyperoptic / Community Fibre
Bunhill | PEREGRINE HOUSE | EC1V 7PR | Cabling complete | Waiting for network build | 211 | Community Fibre
Canonbury | HASLAM HOUSE | N1 2HT | Survey pack approved | Awaiting installation dates | 12 | Hyperoptic
Canonbury | CHANNEL ISLANDS ESTATE | N1 2PR | Cabling complete | Waiting for network build | 190 | Community Fibre
Canonbury | DOUGLAS ESTATE | N1 2PS | Cabling complete | Waiting for network build | 27 | Community Fibre
Finsbury Park | MEDINA COURT | N7 7PU | Survey pack approved | Works on site November | 15 | Hyperoptic
Finsbury Park | ANDOVER ESTATE - Docura, Didbin and Noll | N7 7RD | Cabling completed at Noll and Didbin | Docura due for installation when scaffold erected | 102 | Community Fibre
Finsbury Park | HOOD COURT | N7 6QS | Survey pack approved | Awaiting installation dates | 24 | Community Fibre
Finsbury Park | HADEN COURT | N4 3HR | Survey pack approved | Awaiting installation dates | 112 | Community Fibre
Finsbury Park | CLIFTON COURT | N4 3PH | Survey pack approved | Awaiting installation dates | 87 | Community Fibre
Hillrise | HILLRISE MANSIONS ESTATE | N19 3PU | Cabling complete | Waiting for network build | 100 | Community Fibre
Hillrise | HIGHCROFT ESTATE | N19 3AH | Survey approved (part estate) | Waltersville Road only has been approved and cabling in August. Further blocks to be submitted for survey | 35 | Community Fibre
Hillrise | HORNSEY RISE ESTATE | N19 3DU | Survey pack approved | Works on site late October | 128 | Community Fibre
Hillrise | NEW ORLEANS ESTATE | N19 3UE | Survey pack approved | Awaiting installation dates | 250 | Community Fibre
Hillrise | REDWOOD COURT | N19 3SN | Survey pack approved | Works on site late October | 40 | Community Fibre
Hillrise | LEYDEN MANSIONS ESTATE | N19 3AW | Survey pack approved | Awaiting installation dates | 56 | Community Fibre
Hillrise | ELTHORNE ESTATE | N19 4AF | Awaiting amended survey | Awaiting installation for Beechcroft Way, St John’s Way, Sanders Way, Partington Close, 100 Holland Walk, Mulkern Road | 251 | Community Fibre
Hillrise | HORNSEY LANE ESTATE | N19 3YJ | Survey pack approved | Works on site November | 173 | Community Fibre
Hillrise | HIGHLANDS ESTATE | N4 5SG | Survey pack approved | Awaiting installation dates | 22 | Community Fibre
Hillrise | HOLLY PARK new build | N4 4AT | Survey pack approved | Awaiting installation dates |  | Community Fibre
Hillrise | LOCHBIE MANSIONS ESTATE | N4 4SB | Survey pack approved | Awaiting installation dates | 25 | Community Fibre
Hillrise | HILLSIDE ESTATE | N19 3UY | Survey pack approved | Works on site November | 81 | Community Fibre
Hillrise | MANCHESTER MANSIONS ESTATE | N19 3NA | Cabling complete | Waiting for network build | 35 | Community Fibre
Hillrise | MIRANDA ESTATE | N19 3UH | Survey approved | Awaiting installation dates | 148 | Community Fibre
Hillrise | COLEMAN MANSIONS | N8 9EJ | Cabling complete | Waiting for network build | 40 | Community Fibre
Holloway | CAMDEN ESTATE | N7 9PZ | Survey approved | Awaiting installation dates | 100 | Community Fibre
Holloway | STOCK ORCHARD CRESCENT | 9TD | Survey approved | Awaiting installation dates | 153 | Community Fibre
Holloway | LORAINE MANSIONS | N7 8ST | Survey approved | Awaiting installation dates | 148 | Community Fibre
Holloway | POLLARD CLOSE | N7 8UD | Survey approved | Awaiting installation dates | 88 | Community Fibre
Junction | HARGRAVE MANSIONS ESTATE | N19 5XN | Survey approved for Community Fibre. Awaiting amended survey pack from Hyperoptic | Awaiting installation dates | 149 | Community Fibre / Hyperoptic
Junction | SYCAMORE COURT | N19 5RS | Surveys approved | Works on site October | 24 | Community Fibre / Hyperoptic
Junction | PEMBERTON GARDENS | N19 5RU | Surveys approved | Awaiting installation dates | 6 | Community Fibre / Hyperoptic
Junction | LONGLEY HOUSE | N19 5HB | Awaiting amended survey | Technical considerations being considered by delivery team | 24 | Hyperoptic
Junction | GIRDLESTONE ESTATE | N19 5DR | Survey pack approved | Works on site October | 64 | Community Fibre
Laycock | BARRATT HOUSE ESTATE | N1 2AH | Live connections available |  | 22 | Community Fibre
St Mary’s and St James’ | PLEASANT PLACE ESTATE - Tufnell, Tiverton, Brookfield, Fowler, Dawlish and Arundel, 9,10-11, 12-13 Pleasant Place | N1 2BS | Cabling complete | Waiting for network build |  | Community Fibre
St Mary’s and St James’ | DEVONSHIRE HOUSE | N1 2BE | Cabling complete | Waiting for network build | 9 | Community Fibre
St Mary’s and St James’ | BAMPTON HOUSE | N1 2BP | Cabling complete | Waiting for network build | 10 | Community Fibre
St Mary’s and St James’ | CARLETON HOUSE | N1 2BQ | Cabling complete | Waiting for network build | 6 | Community Fibre
St Mary’s and St James’ | SPRIGGS HOUSE ESTATE | N1 2AJ | Live connections available |  | 38 | Community Fibre
St Mary’s and St James’ | TYNDALE MANSIONS ESTATE | N1 2XG | Cabling complete | Waiting for network build | 25 | Community Fibre
St Mary’s and St James’ | HIGHBURY MANSIONS ESTATE | N1 2XF | Survey approved | Waiting for installation date | 12 | Community Fibre
St Mary’s and St James’ | HAWES STREET | N1 2UU | Survey approved | Waiting for installation date | 49 | Community Fibre
St Mary’s and St James’ | 273 UPPER STREET | N1 2UA | Cabling complete | Waiting for network build | 3 | Community Fibre
St Mary’s and St James’ | WAKELIN HOUSE ESTATE | N1 2EF | Cabling complete | Waiting for network build | 66 | Community Fibre
St Mary’s and St James’ | SEBBON STREET | N1 2EH | Survey approved | Waiting for installation date | 26 | Community Fibre
St Mary’s and St James’ | HALTON ROAD | N1 2EN | Survey approved | Waiting for installation date |  | Community Fibre
St Mary’s and St James’ | HALTON MANSIONS | N1 2BX | Cabling complete | Waiting for network build | 152 | Community Fibre
St Mary’s and St James’ | HUME COURT | N1 2EQ | Survey approved | Waiting for installation date | 36 | Hyperoptic
St Mary’s and St James’ | BARING COURT | N1 3DR | Cabling complete | Waiting for network build | 30 | Hyperoptic
St Mary’s and St James’ | CUMMING ESTATE | N1 8QA | Live connections available |  | 25 | Hyperoptic
St Mary’s and St James’ | SHEPPERTON ROAD | N1 3DH | Amended survey pack approved | The proposal includes listed buildings |  | Hyperoptic
St Mary’s and St James’ | ARBON COURT | N1 7AP | Live connections available |  | 22 | Hyperoptic
St Mary’s and St James’ | RICHMOND GROVE | N1 2DL | Cabling complete | Waiting for network build | 25 | Hyperoptic
St Peter’s and Canalside | FALCON COURT | N1 8EY | Live connections available |  | 22 | Hyperoptic
St Peter’s and Canalside | LANGDON COURT | EC1V 1LH | Live connections available |  | 36 | Hyperoptic
St Peter’s and Canalside | KINGS SQUARE | EC1V 8BA | Survey approved | Works due on site | 372 | Community Fibre
St Peter’s and Canalside | JESSOP COURT | N1 8LG | Survey pack under review |  |  | Hyperoptic / Community Fibre
St Peter’s and Canalside | BOREAS WALK | N1 8DX | Works on site | Waiting for installation date | 6 | Hyperoptic
St Peter’s and Canalside | CLUSE COURT | EC1V 3RB | Survey approved | Waiting for installation date | 212 | Hyperoptic
St Peter’s and Canalside | COLINSDALE | N1 8DZ | Survey approved | Works on site November | 50 | Hyperoptic
Tollington | ALBERMARLE MANSIONS | N7 6JA | Survey approved | Waiting for installation date | 16 | Hyperoptic
Tollington | HOLLY PARK ESTATE | N4 4BW | Awaiting survey | No installation date available | 121 | Community Fibre
Tollington | BENNETT COURT ESTATE | N7 6BN | Survey approved | Works on site November | 112 | Hyperoptic
Tollington | CROUCH HILL COURT | N19 4EN | Survey approved | Works on site November | 140 | Hyperoptic
Tufnell Park | HOLBROOKE COURT ESTATE | N7 0BF | Survey approved | Works on site November | 80 | Hyperoptic
Tufnell Park | TUFNELL PARK ESTATE | N7 0PG | Cabling complete | Waiting for network build | 141 | Community Fibre
Tufnell Park | TANSLEY CLOSE ESTATE | N7 0HP | Survey approved | Works on site November | 37 | Community Fibre
Tufnell Park | BRECKNOCK ROAD ESTATE | N19 5AS | Cabling complete | Waiting for network build | 158 | Community Fibre
Tufnell Park | WILFRED FIENBURGH COURT | N7 0EX | Cabling complete | Waiting for network build | 33 | Community Fibre
Tufnell Park | DAREN COURT | N7 0EN | Cabling complete | Waiting for network build | 90 | Community Fibre
Tufnell Park | HILLDROP ESTATE | N7 0QT | Survey pack approved | Waiting installation date | 75 | Community Fibre
Tufnell Park | 2 and 4 DALMENEY AVENUE | N7 0FN | Survey pack approved | Waiting installation date | 16 | Community Fibre
Tufnell Park | 275 CAMDEN ROAD | N7 0JN | Survey pack approved | Waiting installation date | 18 | Community Fibre
Tufnell Park | MARGARET BONDFIELD | N7 0JB | Cabling complete | Waiting for network build | 10 | Community Fibre
Tufnell Park | MOELWYN HUGHES COURT | N7 0HU | Cabling complete | Waiting for network build | 42 | Community Fibre
Junction | BOWERMAN COURT | N19 3RP | Survey approved | Works on site November | 32 | Hyperoptic
6455